## Read
Project Title: |  | Harsh Environment Sensor Board Part II
No | Student Name ( First, Last ) | email | Faculty (First, Last) | email
1 | Jordan Anger | Jordananger66@gmail.com | Wilfrido Moreno | wmoreno@usf.edu
2 | Jasper Everitt | everittj@usf.edu
3 | Anthony Sedore | amsedore@usf.edu
4 | Joseph Portera | jportera@usf.edu
Please DO NOT change the format of this template
For any update or changes instructor will provide update to the template, as deemed necessary.
File Name should be : Project Name Titles_Last Names or initials of team members
This report is cumaltive, and you should add/update this and submit to canvas. Add extension to it to align with the report number due.
Please work with your team member(s) to update this and weekly basis, the purpose of this sheet is to keep all team members aligned and up to date.

## Accomplishments
Tri-Weekly status. The content of the weekly communication is: a) Program schedule, technical and cost status b) Significant accomplishments c) Issues and resolution plans d) Action items status e) Provide date and time of meeting with the advisor The purpose of this document is for the individual function Team/leads to provide current status in their specific area to be included in the project status Need to provide progress against, at minimum: SRD, SRR, PDR, Website, schedule, WBS, BOM etc.
This Column tracks your significant accomplishments. You can use this to sub-tasks from your scheduled progress.
# | Week of Accomplishments | Description of Accomplishment | Notes
1 | 2024-03-10 | Meet with industry sponsor on wednesday at 16:30.
2 | 2024-03-10 | Create a list of common environment parameters.
3 | 2024-03-10 | Researched other variants of the ESP 32 | Some variants include ESP32 microcontrollers that are standardized with other sponsor's products that are also smaller than the prior microcontroller used
4 | 2024-03-10 | Researched hardware components for use in upcoming PCB design changes
5 | 2024-03-10 | Created a Team cloud folder in Fusion 360 for upcoming design work on the PCB | Cloud document allows all team members to work on PCB design together
6 | 2024-03-10 | Obtained current design files from industry sponsor
7 | 2024-03-25 | First prototype for working PCB was finished
8 | 2024-03-25 | More progress on 3D model in Fusion 360 | Jordan made great progress on this accomplishment
9 | 2024-04-15 | Good progress on PCB design and wiring
9 | 2024-04-08 | First iteration of Bill of Materials completed and added to tri-weekly report
10 | 2024-06-30 | Schematic and BOM completed, submitted for build and order
11 | 2024-08-10 | First prototype boards built
12 | 2024-09-07 | Prototypes inspected for adherance to schematic
13 | 2024-09-18 | Second Revision complete

## Action Register
Minimum one action item per team member per week | [7 empty] | Provide short status in a bulletize forms Closure plans? Why delay?
# | Date Created | Originator | Description | Assignee | Original Due Date | Status | Updated Due Date | Status and Closure Comments | Aging
1 | 2024-02-12 | Joseph | Reach out to previous design team members | Jordan | 2024-02-19 | Complete |  | Contacted previous group members to establish a line of communication to resolve potential design conflicts with previous work.
2 | 2024-02-12 | Joseph | Contact Industry sponsor to schedule week's meeting | Anthony | 2024-02-19 | Complete |  | Meeting was held as planned with industry sponsor.
3 | 2024-02-12 | Joseph | All group members download autodesk and familiarise | All Members | 2024-02-19 | Complete |  | Downloaded
4 | 2024-02-12 | Joseph | Provide availabillity to advisor | All Members | 2024-02-19 | Complete |  | Availabillity Provided.
5 | 2024-03-10 | Joseph | Meet with industry sponsor on wednesday at 16:30 | All Members | 2024-03-10 | Complete |  | Meeting held. Action items received.
6 | 2024-03-13 | Joseph | Create a list of common parameters such as temperature, vibration, humidity etc.. that our device might experience in its native environment. | Jasper | 2024-03-19 | Complete |  | List creation is complete. Next, need to organize and analyze data.
7 | 2024-03-13 | Joseph | Research other variants of the ESP 32 boards that might better suit our application | Anthony | 2024-03-19 | Complete |  | created a list of ESP 32 motherboars and thier various features.
8 | 2024-03-13 | Joseph | Research hardware components for use in upcoming PCB design changes, these include batteries, transistors, sensors etc.. | Jordan | 2024-03-19 | Complete |  | Found multiple Lithium Battery architectures we can use for our application. Will require charging circuit design change. Found some additional components for use with the buck/boost converter.
9 | 2024-03-13 | Joseph | Create a Team cloud folder in Fusion 360 for upcoming design work on the PCB | All Members | 2024-03-13 | Complete |  | Folder created, files inserted.
10 | 2024-03-13 | Joseph | Obtain current design files from industry sponsor | Joseph | 2024-03-13 | Complete |  | Files obtained from Kevin Wolf
11 | 2024-03-19 | Joseph | Obtain all of the 3D models for the components used in our design | Joseph | 2024-04-15 | In Progress |  | 3D Models for specific building blocks on PCB prototype
12 | 2024-03-19 | Joseph | Modeling PCB components in Fusion 360 | Jordan | 2024-04-15 | In Progress |  | Selected common components for capacitors, resistors
13 | 2024-03-19 | Joseph | Work on first couple prototypes of PCB | All Members | 2024-04-28 | In Progress | 2024-05-15 | Plan to get a couple prototypes made and touch base with advisor too see if it fits enclosure and requirements
14 | 2024-03-25 | Anthony | Start assembling BOM (Bill of Materials) | Jasper | 2024-04-21 | Complete | 2024-04-15 | Excel file with preexisting component selection
15 | 2024-04-15 | Joseph | Finish up 3D model for PCB in fusion 360 | Jordan | 2024-04-28 | In Progress |  | Finalize design of the PCB such as its size and width
16 | 2024-04-15 | Joseph | Finish PDR and present to sponsor | All Members | 2024-04-26 | In Progress
17 | 2024-04-15 | Joseph | Test Prototype PCBs with sensor and communication modules | All Members | 2024-05-15 | In Progress |  | Test communication module, battery charging, microcontroller usage
18 | 2024-04-15 | Joseph | Finalize SRD with Analysis Models | All Members | 2024-04-21 | In Progress
19 | 2024-04-10 | Jasper | Print first iteration of BOM from Fusion 360 design file | Jordan | 2024-04-15 | Complete
20 | 2024-08-30 | Jordan | Find booster replacement for schematic with larger area | Jasper | 2024-10-30 | In Progress
21 | 2024-08-30 | Anthony | biweekly reporter file | Anthony | 2024-08-30 | Complete
22 | 2024-08-30 | Anthony | CRD Document Initialization | Joseph | 2024-10-15 | In Progress
23 | 2024-08-30 | Jordan | Receive and inspect prototype pcb | Jordan | 2024-09-15 | Complete
24 | 2024-09-03 | Joseph | Begin Critical Assessment Document | All Members | 2024-10-08 | In Progress
25 | 2024-09-10 | Jordan | Test prototype PCB compatibility with basic software | Anthony | 2024-09-24 | Complete
26 | 2024-09-17 | Jordan | Refine Design and Finalize Schematic | All Members | 2024-10-29 | In Progress
27 | 2024-09-17 | Anthony | biweekly reporter file | Jasper | 2024-09-18 | Complete

## Project Schedule
|  | Desing I | [16 empty] | Design II - subject to change per design II Intructor
Week |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33
Intructors Milestones
Intructors Milestones | bar: Desing I 11; Desing I 16
[12 empty] | SRD due |  |  |  |  | PDR |  |  |  | CDR | [11 empty] | Design Demonstration
Team Formation and Advisor established | bar: Desing I 3 to Desing I 4
WBS, Org. and Schedule due, embeded in excel |  | Desing I 4: TRI Weekly Report 1
Requirements Doc Due ( Preliminary & Final ) |  | Desing I 7: TRI Weekly Report 2
Final Document Package due | bar: Desing I 16 to Desing I 17
Planning and Systems Engineering | Planning and Systems Engineering | [33 empty] | < Please modify this section of schedule per your project
Product Idea/Concept | bar: Desing I 1
System Engineering Managent Plan | bar: Desing I 2
Design Document | bar: Desing I 2
System Electrical Design | bar: Desing I 1 to Desing I 11
System 2D Design | bar: Desing I 11
System 3D Desgin | bar: Desing I 11
Prototype production | bar: Desing I 12 to Desing I 13
System Electrical Design V2 | bar: Desing I 17 to Design II - subject to change per design II Intructor 22
System 2D Design V2 | bar: Design II - subject to change per design II Intructor 23
System 3D Desgin V2 | bar: Design II - subject to change per design II Intructor 23
Prototype production V2
Final Product Production
Sub Design and Development Tasks | Sub Design and Development Tasks
Obtain Software (AutoDesk + EagleCad)
Software Training | bar: Desing I 1
Bill Of Materials V1 | bar: Desing I 5 to Desing I 11
Bill Of Materials V2 | bar: Desing I 14 to Desing I 17
Assumptions:
1. List critical schedule assumptions, dependcies

## WBS
Team | Need to break down task so a single individual is responsible. For example, EE task can be broken for two individuals or more, as needed | By writing this, team member agrees to the task assignment | By writing this, team member agrees to the task assignment
Roles | Responsible Individual | TASK DESCRIPTION - Design I | TASK DESCRIPTION - Design II
MANAGEMENT
Technical Leader | Jordan Anger | write the perceived detail | write the perceived detail
Team Coordination Leader | Joseph Portera | Focus on keeping group coordinated on projects | Focus on keeping group coordinated on projects
Cost & Schedule leader | Jasper Everitt |  | Docummenting costs, expanses, and BOM.
PCB Leader | Anthony Sedore |  | Keeping track of deadlines for group
SYSTEM ENGINEERING
SYST ENGINEERING | Anthony Sedore | Example: SEMP Document | CDR Documnent
SYST ENGINEERING | Jasper Everitt | Example: Requirements Documents
TEST ENGINEERING | Jordan Anger
PROD ENGINEERING | Joseph Portera |  | Help get PCB into manufacturing production for scale
CONFIG MGMT | Joseph Portera
RELIABILITY | Jasper Everitt
QUALITY | Jordan Anger
PARTS MANAGEMENT | Jordan Anger
EMI / EMC | Anthony Sedore | Electromagnetic compatibility
SAFETY | Joseph Portera
Hardware
ELECT.DESIGN
DESIGN | Joseph Portera | Help with PCB design
MECH. DESIGN
PSNA DESIGN | Jasper Everitt
SOFTWARE
SW DEVELOPM | Anthony Sedore | Connecting the pcb board with cellular communication and application | Connecting the pcb board with cellular communication and application & software libraries
TEST Engineering
Test | Jordan Anger |  | testing PCB solder joints and adherance to schematic
TEST SOFTWARE
DESIGN | Anthony Sedore |  | testing/flashing/bugfixxing code

## BOM
Index | Component Name | Short description | function, how it is used in your system | Quantity | Cost | Reference or links to websites
1 | LM1117MPX-3.3 | 3.3v voltage regulator | 3.3v voltage regulator | 1 | 1.14 | https://www.digikey.com/en/products/detail/texas-instruments/LM1117MPX-3.3%2FNOPB/1010516?utm_adgroup=Texas%20Instruments&utm_source=google&utm_medium=cpc&utm_campaign=PMax%20Shopping_Supplier_Texas%20Instruments&utm_term=&utm_content=Texas%20Instruments&utm_id=go_cmp-17816159938_adg-_ad-__dev-c_ext-_prd-1010516_sig-CjwKCAjwoPOwBhAeEiwAJuXRh5CsAdxNsiVsjklsdO8a7qhVnFG-a_a7q8cU8_BmNmhq_jnLatYjUBoCsPsQAvD_BwE&gad_source=1&gclid=CjwKCAjwoPOwBhAeEiwAJuXRh5CsAdxNsiVsjklsdO8a7qhVnFG-a_a7q8cU8_BmNmhq_jnLatYjUBoCsPsQAvD_BwE
2 | SCHOTTKY-DIODESMD | SCHOTTKY-DIODE | Rectification for boost converter | 1
3 | USB_C16PIN | Vertical USB Connector | Charging, Data input/output | 1
4 | C-USC0805 | Capacitor 10nF |  | 1
5 | SCHOTTKY-DIODESMD | SCHOTTKY-DIODE | Rectification for boost converter | 1
6 | L-USL1812 | Inductor 2.2uH |  | 1
7 | CPOL-USUD-6 | Capacitor 220uF |  | 1
8 | R-US_R0805 | Resistor 2k |  | 1
9 | R-US_RO805 | Resistor 330 |  | 1
10 | CPOL-USE5-10.5 | Capacitor 680uF |  | 1
11 | PPTC_6V2A | 6V/2A |  | 1
12 | JST_6_PIN_HORIZONTAL | BMO6B-SRSS-TB |  | 1
13 | CDRH127/LD | CDRH127/LD |  | 1
14 | CH340C | CH340C |  | 1
15 | DHT22 | DHT22 |  | 1
16 | ESP32-WROVER-E-N4R8 | ESP32-WROVER-E-N4R8 |  | 1
17 | JUMPER-SMT_2_NO_SILK | JUMPER-SMT_2_NO_SILK |  | 1
18 | LM2596S | LM2596S |  | 1
19 | MAX40200 | MAX40200 |  | 1
20 | MCP73831 | MCP73831 |  | 1
21 | SIM7000A | SIM7000A |  | 1
22 | XC9148 | XC9148 |  | 1
23 | JP1E |  |  | 1
24 | C-USC0805 | Capacitor 0.1uF |  | 2
25 | C-USC0805 | Capacitor 1uF |  | 2
26 | C-USC0805 | Capacitor 4.7uF |  | 2
27 | R-US_RO805 | Capacitor 5.1k |  | 2
28 | C-USC0805 | Capacitor 10uF |  | 3
29 | 640456-2 | 640456-2 |  | 4
30 | R-US_RO805 | Resistor 1M |  | 5
31 | 5988170107F | 5988170107F |  | 5
32 | TPB1 | TPB1 |  | 7
33 | R-US_RO805 | Resistor 330 |  | 7